## 2021 Activity Log
2021 Master Plan Implementation Activity Log
Strategy Number | Strategy Description | Target Completion Date | Responsible Departments | Status
NR-3 | Identify and protect the remaining agricultural soils to support future food production opportunities and to preserve the remaining rural aspects of the community’s history. | On-going | Conservation Commission and Planning Board | No action taken to date; recommend postponing until 2022. Should be a one-time activity.
NR-6 | Review and revise curriculum and programs in the schools. Suggested revision: Work with Pollard School on Arbor Day and Earth Day celebrations. Monitor state or federal program availability for K-12 students. | On-going | Timberlane Regional School District and Conservation Commission | Conservation Commission works with Pollard School 5th graders each year to celebrate Arbor Day (typically last Friday in April). This year only the 5th grade poerty contest was held. The poster contest and tree plainting were cancelled due to pandemic and school schedules. Recreation Commission is doing something on Earth Day; 4/14/21. Suggest revised strategy as shown in red.
NR-5, NR-7, NR-8, NR-9 | Suggested revision: Work with the Conservation Commission and Recreation Department to develop a plan to provide education to the public and schools using the natural and cultural resources of the Town. | On-going | Planning Board, Recreation Department and Conservation Commission. | No action taken to date; recommend combing these 4 strategies into a single on-going strategy as shown in red.
WR-2 | Expand outreach and engagement to address conservation measures… | On-going | Conservation Commission and Planning Board | No action taken to date. Suggest developing the plan in 2022 with on-going activities after 2022.
WR-6 | Collaborate with neighboring communities on MS4 activities. | On-going | Board of Selectmen, Planning Board, and Conservation Commission | Plaistow collaborates with NHDES sponsored Lower Merrimack Valley Stormwater Coalition (LMVSC). The LMVSC has met 3 or 4 times so far in 2021. Dee Voss and Joel Detty, who works for Normandeau, help with MS4.
WR-11 | Continue to encourage residential private well testing for property owners in Plaistow. | On-going | Conservation Commission and Dept of Health | The Plaistow Health Dept. (Dennise Horrocks) conducts such a testing program in conjunction with NHDES every other year. It was last done in the spring of 2020.
WR-13 | Continue to provide outreach to homeowners related to household hazardous waste. | On-going | Board of Selectmen and Highway Department | Plaistow’s Highway Dept. works with surrounding towns to provide semi-annual hazardous waste collection days. The April collection is in Plaistow at PARC and in October in the other participating towns.
WR-14 | Continue to implement Best Management Practice (BMP) assessment program for businesses in Plaistow. | On-going | Conservation Commission and Building Inspector | No action to date. The BMP program was developed as part of the Source Water Protection Program (developed by the Conservation Commission in 2000). The program involves the Building Inspector to make inspections of businesses every 3 years. Program needs to be reactivated.
WR-15 | Continue to install signage relating to drinking water source protection areas. | On-going | Conservation Commission and Highway Dept. | The Conservation Commission purchased watershed signs and had the Highway Dept. install them in appropriate places. Because Plaistow does not have any municipal water supplies, this strategy should be deleted.
WR-16 | Promote Plaistow Pride days as a Town-wide effort to clean up neighborhoods and roadways and prevent potential contamination of our groundwater. | On-going | Board of Selectmen, Highway Dept. and Recreation Dept. | To be held this year on April 24th. The Recreation Dept. is a major sponsor of this event.
OS-3 | Actively participate with regional organizations that support acquisition and protection of open space such as the regional planning commissions and Rockingham Land Trust. | On-going | Planning Board and Conservation Commission | Plaistow actively participates with the Rockingham Planning Commission, Southeast Land Trust (SELT - who owns the conservation easment on the Town Forest properties and does annual monitoring) and the Rockingham Couny Conservation District (who owns a conservation easemnt on the former Cox farm - approximately 20 acres and also does annual monitoring). The monitoring typically takes place in the fall of each year.
OS-5 | Continue to allocate an established amount to the funding of the Conservation fund each year. Suggested revision: Annually monitor the fund balances in the Conservation Fund, the Current Use Fund and the Forestry Fund to ensure the funds have a sufficient balance for purchase of conservation lands and/or easements. | On-going | CIP Committee and Conservation Commission | This activity is done during the 2nd half of the year. The CIP Committee monitors all capital related funds. The Conservation Commissions decides if the fund balances are sufficient. Fund deposits will only be made when the balances are not sufficient and therefore a suggested revision is shown in red.
OS-6 | Apply for grants and technical assistance available through non-profit state and federal agencies for open space protection. | On-going | Board of Selectmen, Planning Board, and Conservation Commission | No action taken to date.
R-5 | The Conservation Commission should coninue to work with represtatives from abutting towns of Atkinson, Hampstead and Kingston to expand on the Town Forest and P.A.R.C. trail systems. | On-going | Conservation Commission and Recreation Commission | The Conservation Commission is working with Atkinson and Hampstead to develop a common "3-Town" trail map. Project on hold pending a review of the trails within the Plaistow and the planned foreset management activity scheduled for 2021. A more formal review of the possibility of connecting to Kingston trails should be undertaken in 2021 or 2022.
P-1 | On even number years, review the Town's current land use regulations in order to determine if the existing regulations adequately encourage the type and location of quality affordable housing in Plaistow. | On-going | Planning Board | No action taken to date in 2021. Review to occur in 2022.
P-5 | Working housing affordability statistics should be reviewed on odd-numbered years to ensure compliance with statutory requirements. The present average rental rate is very close to the maximum allowable rent, which further justifies the odd-numbered year review. | On-going | Planning Board | No action taken to date.
CF-1 | Establish a capital reserve fund for the purpose of providing a steady source of funding for building and grounds maintenance | 2020 | CIP Committee, BOS, Budget Committee | No support in 2020 or 2021. CIP Committee meetings typically start in the early summer at which time this recommendation will again be reviewed.
CF-2 | Perform periodic inspections of all buildings and note problems that need to be addressed. | On-going | Building Maintenance Supervisor | If major repairs/upgrades are needed the Building Maintenance Supervisor informs the CIP Committee.
CF-3 | Perform energy audits of all buildings where appropriate and note structures and systems that are not energy efficient. | 2020 | Energy Committee, CIP Committee, BOS, | This acivity has been completed and should be either removed from the list or mark it as complete.
CF-4 | Perform periodic inspections of the cemetery and note problems that need to be addressed. | On-going | Cemetery Sexton, Town Manager | No action taken to date, new projects if needed are usually reported to the CIP Committee.
CF-5 | Perform annual inspections of all police department vehicles and replace those that can no longer perform their assigned duties safely or with excessive maintenance costs. | On-going | Police Chief, Town Manager | No action to date. The list of police vehicles used by the Chief, by detectives, and for patrol is sent to the CIP Committee usually in mid-summer.
CF-6 | Perform annual inspections of all fire department vehicles and replace those that can no longer perform their assigned duties safely or with excessive maintenance costs. | On-going | Fire Chief, Town Manager | No action to date. The results of the inspections are reported to the CIP Committee usually in mid-summer.
CF-7 | Maintain fire department vehicle rotation schedule and the associated capital reserve fund and impact fee fund balances. | On-going | CIP Committee, Fire Chief | No action to date. The rotation schedules and fund balances are reported to the CIP Committee usually in mid-summer.
CF-8 | Make an annual deposit into the fire department vehicle capital reserve fund and monitor the fund balance to ensure there is sufficient funding to maintain the vehicle rotation schedule. | On-going | CIP Committee, Fire Chief, BOS, Budget Committee | No action to date. The deposit amounts are initially determined by the CIP Committee usually in mid-summer.
CF-9 | Perform annual inspections of all highway department vehicles and replace those that can no longer perform their assigned duties safely or with excessive maintenance costs. | On-going | Highway Supervisor, Town Manager | No action to date. The results of the inspections are reported to the CIP Committee usually in mid-summer.
CF-10 | Maintain highway department vehicle rotation schedule and the associated capital reserve fund and impact fee fund balances. | On-going | CIP Committee, Highway Supervisor | No action to date. The rotation schedules and fund balances are reported to the CIP Committee usually in mid-summer.
CF-11 | Make an annual deposit into the highway department vehicle capital reserve fund and monitor the fund balance to ensure there is sufficient funding to maintain the vehicle rotation schedule. | On-going | CIP Committee, Highway Supervisor, BOS, Budget Committee | No action to date. The deposit amounts are initially determined by the CIP Committee usually in mid-summer.
CF-12 | Automate cemetery records and verify the automated records match the physical cemetery plots. | On-going | Cemetery Sexton | Update not yet available.
CF-17 | Adopt zoning, subdivision, site plan regulations to account for a potable water system | 2020 | Planning Board | Activity not yet complete.
CF-18 | Adopt a new road profile that accounts for a potable water line, underground utility lines, and gas lines. | 2020 | Planning Board, Water Consultants | Activity not yet complete.
T-2 | Apply for Transportation Alternative Program (TAP) funds, through the NH Department of Transportation (NHDOT), for the construction of sidewalks and multi-use paths along state and local routes. | On-going | Planning Board & BOS | No action to be taken in 2021 or 2022. The next round of TAP applications will not occur until 2023.
T-4 | When adopting changes to Plaistow's land use regulations, consider promoting mixed-use development so that daily activities are integrated rather than separated. Activities that are separated require vehicle trips between zones, reducing the ability to walk/bike between destinations. Suggested rewrite: Identify mixed-use zoning opportunities that allow residents to walk or bike to employment, education, entertainment and/or recreational facilities. | On-going | Planning Board | Mixed use with multi-family residential was added as a permitted in 2021 newly defined CI Overlay District.
T-7 | On an annual basis, establish capital projects that should be included in the Town's Capital Improvements Program. Such projects would include roadway maintenace and improvements that are consistent with the Town's Master Plan and alternative transportation mode projects including facilities for pedestrians, bicycles and transit. The Capital Improvements Program should identify a methodology for prioritizing projects which emphasize the importance of maintaining the existing roadway systems as well as intersection improvements. | On-going | BOS, Budget Committee, CIP Committee | The Town's RSMS program required funding is inluded annually in the CIP. No other action taken to date and none expected for 2021 or 2022. The Transformation Infrastructure Capital Reserve Fund is nearly depleted and most transportation related funding opportunities require a 20%, 30% or 50% local match.
T-8 | Work with the NHDOT on Context Sensitive Solutions for roadway improvements in Plaistow. | On-going | BOS, Highway Safety Committee | Town boards and committees are providing input/comments for the Main St traffic calming project being managed by NHDOT.
T-10 | Work with local employers to encourage Transportation Demand Management (TDM) programs for employment centers and new paving solutions. | On-going | Planning Board, PACE, Merrimack Valley Chamber of Commerce | No such opportunities will exist in 2021 and no action will be taken.
FLU-9 | Research alternatives to sewage treatment along the Rt 125 corridor so that the Town can coordinate a new developmet patternalong this corridor. | On-going | BOS, Planning Board | No action taken to date.